## Product Backlog
PRODUCT BACKLOG. TEAM 12 Bin Chickens
ID | ITEM | TASK ID | TASK | ASSIGNED TO | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a doctor I want to verify myself as a doctor using an accreditation number So that I can create a doctor account for myself | 1.1 | Make the database with registration table |  | High | 5 | In progress | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
1 |  | 1.2 | Create GUI for landing page (see wireframe)
1 |  | 1.3 | Verify that input is 'legal'/satisfies business requirements (has accreditation number)
1 |  | 1.4 | Verify that doctor is not already in the database
1 |  | 1.5 | Create new doctor row in the database if a) legal and b) not already registered (added as 'active' but pending approval)
1 |  | 1.6 | Redirect to 'waiting approval' page
2 | As an administrator I want to verify the doctor's accreditation number So that I can approve the doctor's account | 2.1 | Create GUI for login page |  | High | 3 | In progress | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
2 |  | 2.2 | Create GUI for doctor verification page
2 |  | 2.3 | Fetch list of all unverified doctors from database (into doctor objects)
2 |  | 2.4 | Display list of all unverified doctors with approval buttons beside
2 |  | 2.5 | When approved, update doctor record within database
2 |  | 2.6 | Make the database with registration table
3 | As an unregistered patient I want to sign up for a ND Telemedicine App account So that I can register with the application. | 3.1 | Create GUI for landing page (see wireframe) |  | High | 5 | In progress | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
3 |  | 3.2 | Verify that input is 'legal'/satisfies business requirements
3 |  | 3.3 | Verify that Patient is not already in the database
3 |  | 3.4 | Create new patient row in the database if a) legal and b) not already registered.
3 |  | 3.5 | Create patient profile object and assign information for the patient that is registering
3 |  | 3.6 | Redirect to the patient home page -> make home page using wireframe as a guide.
4 | As a patient I want to add information to my profile So that I can add my health information for my doctor. | 4.1 | Create the health information table(s) in the database |  | High | 5 | In progress | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
4 |  | 4.2 | Create health information GUI page
4 |  | 4.3 | Display current patient information (stored in patient object) in the GUI.
4 |  | 4.4 | Save patient information to the database row after changes or additions have been made (also handed back to patient object)
5 | As a doctor I want sign up for a ND telemedicine App account So that I can register with the application | 5.1 | Make the database with registration table. |  | High | 5 | In progress | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
5 |  | 5.2 | Create GUI for landing page (see wireframe)
5 |  | 5.3 | Verify that input is 'legal'/satisfies business requirements
5 |  | 5.4 | Verify that doctor is not already in the database
5 |  | 5.5 | Create new doctor row in the database if a) legal and b) not already registered (added as 'active' but pending approval)
5 |  | 5.6 | Redirect to 'waiting approval' page
6 | As an administrator I want to register accounts using an API So that I can register users more quickly than using the GUI | 6.1 | Setup API gateway |  | High | 8 | Ongoing | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
6 |  | 6.2 | Make the database with registration table.
6 |  | 6.3 | Create GUI for landing page (see wireframe)
6 |  | 6.4 | Verify that input is 'legal'/satisfies business requirements
6 |  | 6.5 | Verify that Patient is not already in the database
6 |  | 6.6 | Create new patient/doctor row in the database if a) legal and b) not already registered
6 |  | 6.7 | Create API endpoint (POST method)
7 | As a patient I want to book a telehealth appointment using the calendar So that I can talk to a doctor about my health. | 7 | Patient can view the calender of the availiabilities of the doctors and book with desired appointment according to the calender |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
8 | As a patient I want to change my health status So that my doctor can know of my condition for an appointment. | 8 | Patients can change their health status in their account |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
9 | As a patient I want to sign in on my ND Telemedicine App account So that I can use the application and its features. | 9 | Patients can sign in using their username and password to access the application's features |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
10 | As a doctor I want to view my patient's profile So that I know my patient's health status for an appointment. | 10 | Patient’s profile information (name, age, gender, etc…) is fetched from the database and includes the patient’s health status Patient’s profile information (name, age, gender, etc…) stored correctly as a temporary object and matches information stored in database. Live updates to database table holding patient’s profile information are reflected in the doctor’s view of the patient profile. |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
11 | As a Doctor I want to create prescriptions for patients so they know what kind of medicine they need. | 11 | - Prescription object is created when valid data is input for: medicine name; patient name; date of prescription; instructions for taking medicine; doctor provider number; doctor name. - Prescription object is not created when invalid data is input for: medicine name; patient name; date of prescription; instructions for taking medicine; doctor provider number; doctor name. - The creation of a prescription object is associated with the correct patient’s profile. - The creation of a prescription object is associated with the correct doctor’s profile. - The creation of a prescription with a valid time input will create a notification object for the patient within the calendar. - The creation of a prescription with an invalid time input will not create a notification object for the patient within the calendar. |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
12 | As a Doctor I want to view the patient's medical history So i can assess the current prescription. | 12 | Patient’s medical history retrieved from database when a match found for patient search input. Patient’s medical history is not retrieved from database when no match is found for input. Medical history object successfully created with all required fields when medical history is retrieved from the database. Medical history object is not created when information retrieved from the database is invalid or has not been retrieved correctly. No medical history objects are created for new patients that have not seen a doctor. |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
13 | As a patient I want to access my prescriptions So that i am able to have a list of all prescriptions that I'm taking at the moment. | 13 | When patient profile accessed, all prescription objects loaded with correct information. When patient profile accessed, some prescription objects loaded with incorrect information. When patient profile accessed, all prescription objects loaded with incorrect information. Fetch for patient prescription information in database returns valid data (all rows; all variables, data only associated with logged-in patient) Fetch for patient prescription information in database returns invalid data (all rows; all variables, data only associated with logged-in patient) When prescription added to database and associated with patient, system creates a new prescription object. When prescription added to database and associated with patient, system does not create a new prescription object. |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
14 | As a Doctor I want to send a prescription to my patients So that they can easily use the medicine. | 14 | Information stored in temporary prescription object is persisted successfully to database. Information stored in temporary prescription object is not persisted successfully to database. Temporary prescription object is created successfully when valid input provided. Temporary prescription object is not created successfully when partial invalid input provided. Temporary prescription object is not created successfully when invalid input provided. |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
15 | As a doctor I want to chat with my patient in real-time So I am able to understand their health situation | 15 | Doctor's name appear in the chat box with the status as online Patients's messages appear on the left side of the chat box and doctor's ones on the right side "Typing..." apprears on the screen when patient is typing Doctor and patient can discuss about the patient's health conditions in the chat |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
16 | As a patient I want to chat with my doctor in real-time So I can discuss with them about my current health situation | 16 | Patient's name appear in the chat box with the status as online Doctor's messages appear on the left side of the chat box and patient's ones on the right side "typing..." apprears on the screen when patient is typing Doctor and patient can discuss about the patient's health conditions in the chat |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
17 | As a doctor I want to add my availabilities for telehealth appointments to the calendar So that I can view all my upcoming my availabilities. | 17 | Availabilities correctly retrieved from database for chosen date Display shows booked appointments, upcoming availabilities, and unavailabilities |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
18 | As a doctor I want to add my availabilities for telehealth appointments to the calendar So that patients can book appointments. | 18 | Availabilities correctly retrieved from database for chosen date Display shows booked appointments, upcoming availabilities, and unavailabilities Adding availability displays correctly and updates appointments table in database |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
19 | As a doctor I want to modify my existing availabilities for telehealth appointments in the calendar So that patients can book appointments when I have additional availability. | 19 | Availabilities correctly retrieved from database for chosen date Display shows booked appointments, upcoming availabilities, and unavailabilities Modifying availability displays correctly and updates appointments table in database |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
20 | As a doctor I want to receive a reminder before an appointment So I don't lose track of time and don't miss any appointments | 20 |  |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
21 | As a patient I want to receive a reminder before an appointment So I don't miss the appointment | 21 |  |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
22 | As an administrator I want to trigger a reset of user passwords So that users can keep their accounts secure. | 22 | All users prompted for password change after reset password trigger (next time login or email?) Password checking: Must have Upper/lowercase letters, numbers and select symbols Legal passwords are saved correctly into database Illegal passwords are not saved into database Database passwords are empty (besides admin) after reset trigger |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
23 | As an administrator I want to manage doctor accounts So that I can deactivate accounts of doctors who left the practice. | 23 | Doctors account status becomes inactive An inactive doctor cannot login to their account An inactive doctor is saved correctly in the database Admin can view list of all current active doctors |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
24 | As a product developer I want to create an ER diagram So I can visually understand the relationship between all components of the application | 24 |  |  | Medium |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
25 | As a doctor I want to cancel telehealth appointments in the calendar So that I can notify the patient that I am no longer able to conduct the appointment | 25 | Doctors appointment can be canceled by the doctors. Patient can see when the doctors are not available. |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
26 | As a patient I want to reschedule my telehealth appointments in the calendar So that I can change my appointment when I need to. | 26 | Patients can change their appointment that already booked to another time |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
27 | As a patient I want to book a telehealth appointment using the calendar So that I can get treatment for my health conditions. | 27 | Patients can book their appointment through the app using a calender that show the available time |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
28 | As a doctor I want patients to book telehealth appointments with me using the calendar So that I can plan my day. | 28 | Doctors allow patients to book an appointment that suits doctors |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
29 | As a patient I want to cancel telehealth appointments in the calendar So that I can change my appointment to suit my schedule. | 29 | Patients can cancel their appointment in the system and update the database with the cancelation |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
30 | As a patient I want to book a telehealth appointment using the calendar So that I can plan my day | 30 | Patients can book an appointment with their doctor when they avaliable |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
31 | As a patient I want to reset my password So that I can recover my account if I forget my user details. | 31 | Patient can request reset the password from the app |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
32 | As a doctor I want to manage my profile So that I can update my doctor bio and details. | 32 | Profile updates when bio and details changed simultaneously Profile updates when doctor bio ONLY is changed Profile updates when doctor details ONLY are changed Profile does not contain dctor information after it has been deleted/removed String checking: A string is not accepted starting with punctuation, numbers (integers, floats etc...) or spaces. String checking: A string is accepted that is formatted correctly (doesn't start with punctuation; numbers; spaces) Legal profile updates are saved in database. Illegal profile updates are not saved in database. |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
33 | As a doctor I want to reset my password So that I can recover my account if I forget my user details. | 33 | When doctor with a profile enters email address, database queried to determine if they are a registered user: returns true flag. When doctor without a profile enters email address, database queried to determine if they are a registered user: returns false flag. Passwords greater than 8 characters are accepted Passwords smaller than 8 characters are rejected Rejected passwords do not result in updates to patient’s profile information stored in database. Rejected passwords result in update to patient’s profile information stored in database. When password successfully updated, user is logged in. When password unsuccessfully updated, user is returned to generic landing page. |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
34 | As a doctor I want to create patient accounts So that I can register patients on their behalf. | 34 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
35 | As a Doctor I want to know if the patients have taken the medicine so i am able to know if the patients follow the medical plan or not. | 35 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
36 | As a patient I want to know if can have a second opinion with my doctor so i am able to use it with suitable time without problems. | 36 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
37 | As a Doctor I want to send a notification to patients about the medical plan #need to be discussed with group so patients can use the medicine in the best time. | 37 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
38 | As a patient I want to know the side effect of each medicine so i am able to use it without concern. | 38 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
39 | As a patient I want to have a note to the medical plan so i am able to be in track with my prescribed medicine. | 39 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
40 | As a patient I want to have a quick follow-up with my doctor So I can discuss how the new medication is going | 40 | -doctor's messages appear on the left side of the chat box and patient's ones on the right side |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
41 | As a doctor I want to have a quick follow up with my patient So I can make sure their new medication is working | 41 | -"typing..." apprears on the screen when patient is typing |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
42 | As a patient I want to have a quick follow-up with my doctor So I can let them know how my symptoms are going | 42 | -doctor and patient can discuss about the patient's health conditions in the chat |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
43 | As a doctor I want to have a quick follow up with my patient So I can make sure their symptoms are getting better *needs to be discussed* | 43 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
44 | As a patient ****This could be too much with the addition of uploading photos**** I want to be able to send a photo to my doctor So we can discuss this bite/rash/bruise/etc on my arm | 44 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
45 | As a doctor I want to review my recent chat with a patient So I can add notes to their file | 45 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
46 | As a patient I want to review my previous chat with my doctor So I can make sure I understand what I need to do regarding my health/remember what they said | 46 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
47 | As a patient I want to chat with my doctor So I can receive a referral to see a specialist | 47 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
48 | As a doctor I want to receive a notification when a patient messages me So I don't miss out on their message | 48 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
49 | As a patient I want to receive a notification when my doctor messages me So I don't miss out on their message | 49 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
50 | As a patient I want to view a calendar display of all available telehealth appointments So that I can see easily which appointments are available. | 50 | Availabilities correctly retrieved from database for chosen date Display shows current availabilities and upcoming appointments (if any) |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
51 | As a doctor I want to add my availabilities for telehealth appointments to the calendar So that patients can view my availabilities. | 51 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
52 | As a doctor I want to add my availabilities for telehealth appointments to the calendar So that I can view all my upcoming availabilities. | 52 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
53 | As a doctor I want to modify my existing availabilities for telehealth appointments in the calendar So that patients cannot book appointments when I am no longer available. | 53 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
54 | As a doctor I want to cancel existing availabilities for telehealth appointments in the calendar So that patients cannot book appointments when I am no longer available. | 54 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
55 | As a patient I want to receive a reminder when an appointment is modified or cancelled So I don't waste time waiting for an appointment and I can plan my day | 55 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
56 | As a doctor I want to receive a reminder when an appointment is modified or cancelled So I can plan my day better | 56 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
57 | As an administrator I want to create doctor accounts So that I can add new doctors to the application system. | 57 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed
58 | As an administrator I want to manage doctor accounts So that I can edit their information on their behalf. | 58 |  |  | Low |  | Not started | Code for user story completed Passes unit tests Conforms to acceptance criteria Meets non-functional requirements Code reviewed Code merged into main (production) branch Product owner accepts user story User story marked as completed

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a doctor I want to verify myself as a doctor using an accreditation number So that I can create a doctor account for myself | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 |  | #N/A | #N/A | #N/A | #N/A | #N/A
5 |  | #N/A | #N/A | #N/A | #N/A | #N/A
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As an administrator I want to verify the doctor's accreditation number So that I can approve the doctor's account | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As an unregistered patient I want to sign up for a ND Telemedicine App account So that I can register with the application. | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a patient I want to add information to my profile So that I can add my health information for my doctor. | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a doctor I want sign up for a ND telemedicine App account So that I can register with the application | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A